## Task list
Phase | Task | Start Date | End Date | Duration | Done? | Include iterations if that's the lifecycle chosen
Design | Create project plan | 2019-02-28 | 2019-03-01 | 1 | X
Design | Read module literature | 2019-02-27 | 2019-03-01 | 2 | X
Design | Choose lifecycle model | 2019-02-08 | 2019-03-01 | 21 | X
Design | Complete literature search | 2019-03-01 | 2019-03-02 | 1 | X
Design | Review literature | 2019-03-01 | 2019-03-02 | 1 | X
Design | Compile project requirements | 2019-03-03 | 2019-03-04 | 1 | X
Design | TMA01 submission | 2019-02-26 | 2019-03-05 | 7 | X
Design | Produce wireframes | 2019-03-03 | 2019-03-10 | 7 | X
Design | Set up Git repo | 2019-03-11 | 2019-03-12 | 1 | X
Design | Set up working environment (IDE) | 2019-03-11 | 2019-03-12 | 1 | X
Testing | Write acceptance tests | 2019-03-13 | 2019-03-17 | 4 |  | See TT284
Planning | Investigate potential existing APIs for integration | 2019-04-01 | 2019-04-04 | 3 | X
Design | Frontend framework investigation | 2019-03-17 | 2019-04-10 | 24 | X
| TMA02 submission | 2019-04-09 | 2019-04-16 | 7 | X
Implementaion | Search recipes code implementation | 2019-04-05 | 2019-04-29 | 24 | X
| Holiday | 2019-04-29 | 2019-05-07 | 8 | X
Design | Responsive design research | 2019-05-08 | 2019-05-29 | 21
Implementation | Responsive CSS implementation | 2019-05-22 | 2019-05-29 | 7
Implementaion | View recipe code implementation | 2019-05-30 | 2019-06-07 | 8 | X
| TM356 revision | 2019-06-07 | 2019-06-13 | 6 | X
Implementaion | View recipe search results code implementation | 2019-06-14 | 2019-06-17 | 3 | X
| Database research and schema implementation | 2019-06-17 | 2019-06-23 | 6
| Holiday | 2019-06-23 | 2019-06-29 | 6 | X
Implementation | Login page and authentication implementation | 2019-06-30 | 2019-07-05 | 5
TMA03 | TMA03 draft project report section | 2019-06-30 | 2019-07-06 | 6
| Food safety information page implementation | 2019-07-06 | 2019-07-08 | 2
TMA03 | TMA03 review section | 2019-07-06 | 2019-07-09 | 3
Implementaion | View store cupboard code implementation | 2019-07-06 | 2019-07-11 | 5
Implementaion | Add store cupboard item code implementation | 2019-07-12 | 2019-07-20 | 8
| Delete/edit store cupboard item | 2019-07-20 | 2019-07-27 | 7
| Hosting research and implementation | 2019-07-27 | 2019-08-12 | 16
Testing | Acceptance testing & fixes | 2019-08-12 | 2019-08-17 | 5
Testing | Cross browser/device testing & fixes | 2019-08-18 | 2019-08-25 | 7
| Write report | 2019-08-28 | 2019-09-11 | 14
| Project submission | 2019-09-11 | 2019-09-11 | 0

## Project tasks
Gather requirements
Create wireframes
Set up work environment
Research responsive design | Flexbox, grid, bootstrap, material? Why did I make the choice I did?
Research JavaScript frameworks and viability
Begin coding HTML pages
Create styles
Test app, methods of testing?